## Slide 1
SECTION 3.1 · QUALITY AND EFFECTIVENESS OF THE WORK PLAN
MERISTIME
From thermosensing to organ timing in the shoot apical meristem
24 months
3 scientific work packages
6 milestones
Notes: Twenty-four month European Fellowship. Three scientific work packages plus training and dissemination.

## Slide 2
Gantt chart
Twenty-four months, host laboratory in Neuchâtel
WORK PACKAGE / TASK
YEAR 1
YEAR 2
MONTH
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
WP1 · Temperature response of the meristem
1.1 Plastochron and phyllotaxis against thermal time
MS2
1.2 Live imaging of meristem and auxin reporters
MS1
WP2 · phyB and redox/NO signalling
2.1 Temperature and redox compartmentalisation
MS3
2.2 Nitric oxide as a candidate temperature transducer
WP3 · Single-cell transcriptomics
3.1 Factorial temperature × thermal-time design, snRNA-seq
MS4
3.2 Analysis and candidate networks
WP4 · Training, dissemination, management
4.1 Career Development Plan and FAIR Data Management Plan
4.2 Training, conferences and outreach
4.3 Co-supervision of a master's student
4.4 Preprints, open access, data deposition
MS5
MS6
Notes: Bars span the months each task is active; MS labels sit on the bar at the month the milestone falls due.

## Slide 3
Milestones
MS1 · MONTH 6
Live-imaging under controlled temperature validated
MS2 · MONTH 10
Thermal-time plastochron dataset, wild type and phyB
MS3 · MONTH 15
Redox/NO map across temperatures and in phyB
MS4 · MONTH 18
Single-nucleus dataset generated and QC-passed
MS5 · MONTH 18
First manuscript submitted (WP1 + WP2)
MS6 · MONTH 23
Second manuscript submitted (WP3), data deposited
WP1 and WP2 overlap deliberately: the redox and NO perturbations of WP2 are read on the thermal-time basis established in Task 1.1, and both feed the first manuscript. WP3 starts once the imaging phenotypes define the thermal-time points to be sampled.
Notes: Six milestones. MS2 is the decisive test of thermal-time compensation; MS4 gates the second paper.